## Sheet1
# | Task | Comments | Time for development(in Hours) | ReCorrect Time After Client meeting(in Hours)
1 | 1. Login Page Adjustments: Change the default login link to just "outrider.net" instead of "/login". Swap the positions of Coinbase and Wallet Connect on the homepage | **Already Developed | 0 | 1
2 | 2. Content Updates: Add content to the "Terms of Service" and "Privacy Policy" pages. | **Please Provide Content for this page ** Content will be displayed on the popup | 5 | 5
3 | 3. User Experience Improvements: After the initial login, users should not be asked for their birthdate again. The "Get Started" prompt should not appear for users who already have an account. Subsequent logins should only require wallet connection, not full login. | **need discussion on this point 1. What is the use of birthDate? 2. Only metamask wallet is working for login, Other wallets have more then 1 options to login and currently not working. | 0 | 8
4 | 4. Feed and Babble Integration: Rename "Feed" to "Babble". Make Babble the default landing page. Ensure all user-associated posts are displayed in a timeline similar to Facebook. Update notification wording to reflect the change to Babble. Position Babble prominently in the navigation menu. | **I have some doubts 1. only personal post should be displayed or also group post ? 2. what are the things should be included in notifications | 60 | 60
5 | 5. Profile Page Enhancements: Improve fonts and comment visibility across the site. Linked content has a preview similar to twitter/X Ensure videos and content have previews. Implement a rewards system where points lead to better badges. | **Need R&D to implement reward systems Time: 30h for development + 40h for R&D | 70 | 70
6 | 6. Cybot Integration: Modify the Cybots feed to show a full feed directly, not just from communities. | **need discussion on this point 1. What are the criteria for the feed posts | 40 | 8
7 | 7.Community and Notifications: Ensure notifications are functioning correctly. Enable dynamic updates. | **need discussion on this point 1. What is dynamic updates? | 40 | 40
8 | 8. Admin and Cybot Access: Grant Admin and Cybot access for report generation and post removal. Cybot/admin can see reported content but cannot click on this or remove unless we go to the page in question. | **Need Admin access to check this functionlity | 30 | 30
9 | 9. Algorithm and Feed: Focus the main feed on Babble, with a top ten list of communities. Allow users to view community-specific content or posts connected to their communities. | - | 40 | 40
10 | 10. Cybot Implementation Using Chat GPT API: Develop a bot named "Cybot" that communicates based on prompts, utilizing Chat GPT's API. Cybot's character: Envision Cybot as a robot cowboy. He should have a unique speaking style that reflects this persona, blending elements of a traditional cowboy dialect with a futuristic, robotic twist. | - | 40 | 40
|  | Total Time for Development | 302 hous